## Plan
# | Task | Description | Category | Sprint(s) | Resource | Commnets
1 | Database design | Create tables required for the project | Database | Sprint 1 | Pranusha and Bharat
2 | Home page | Create a home page to reflect colours and styles of Resilience website - logo and font style - Use the best availabile one | User -UI | Sprint 1 | Harish
3 | Validation page | Refer - 1. User Validation and Authentication in the Use_case_flow document | User -UI | Sprint 1 | Harish
4 | Signup page | Refer - 1. User Validation and Authentication in the Use_case_flow document | User -UI | Sprint 1 | Harish
5 | Data insertion | Refer - 1. User Validation and Authentication in the Use_case_flow document | Services | Sprint 2 | Pranusha
6 | Sign-in page | Refer - 1. User Validation and Authentication in the Use_case_flow document | User -UI | Sprint 1 | Harish
7 | User validation | Refer - 1. User Validation and Authentication in the Use_case_flow document | Services | Sprint 2 | Pranusha
8 | User authentication | Refer - 1. User Validation and Authentication in the Use_case_flow document | Services | Sprint 2 | Pranusha
9 | Survuy UI | Refer - 2. Survey Form and Services in the Use_case_flow document | User -UI | Sprint 1 | Harish and Pranusha
10 | Survy UI functionality | Refer - 2. Survey Form and Services in the Use_case_flow document | Services | Sprint 2 and 3 | Pranusha
11 | Survey results UI | Refer - 3. Survey Results UI in the Use_case_flow document | User -UI | Sprint 2 and 3 | Harish and Bharath
12 | Employees Data upload | Refer - 4. Employees Data upload in the Use_case_flow document | Admin -UI | Sprint 1 | Harish
13 | Employees Data upload functionality | Refer - 4. Employees Data upload in the Use_case_flow document | Services | Sprint 1 | Bharath
14 | Release Survey | Refer - 5. Release Survey UI and Functionality in the Use_case_flow document | Admin -UI | Sprint 3 | Harish
15 | Release Survey functionality | Refer - 5. Release Survey UI and Functionality in the Use_case_flow document | Services | Sprint 3 | Bharath
16 | Survey Questionnaire data upload | Refer - 6. Survey Questionnaire data upload in the Use_case_flow document | Admin -UI | Sprint 1 | Harish
17 | Survey Questionnaire data upload Functionality | Refer - 6. Survey Questionnaire data upload in the Use_case_flow document | Services | Sprint 2 | Bharath
18 | Visualization | Refer - 7. Visualization in the Use_case_flow document | Services | Sprint 2, 3 and Sprint 4 | Bharath ,Harsha and Pranusha
19 | Automation reports | Refer - 8. Automation reports in the Use_case_flow document | Services | Sprint 5 | Pranusha and Bharat
20 | Pdf report generation | Refer - 9. Pdf report generation in the Use_case_flow document | Services | Sprint 5 | Pranusha and Bharat

## Sprint dates
Sprint | Start date | End date | Ineternal Demo date | Client Demo date | High level Deliverables
Sprint1 | 2018-12-22 | 2019-01-04 | 2019-01-05 | 2019-01-10 | • All the Screens – All the screens with test/hardcoded data • UI Navigations – UI navigations with test/hardcoded data • Data upload functionality with sample data • Physical and technical flow diagrams
Sprint2 | 2019-01-06 | 2019-01-19 | 2019-01-20 | 2019-01-22 | • UI navigations – UI navigations with end-end flow • Data and Q&A upload functionally • Working Survey functionality • Sample reports –Few reports
Sprint3 | 2018-01-21 | 2019-02-02 | 2019-02-03 | 2019-02-07
Sprint4 | 2018-02-03 | 2019-02-21 | 2019-02-22 | 2019-02-23 | • Bug fixes – All the identified fixes from stage 1 phase • UI navigations – UI navigations with end-end flow • Data and Q&A upload functionally complete flow • Working Survey functionality complete flow • Visualization –Complete flow • Automated reports – Complete flow
Sprint5 | 2019-02-24 | 2019-03-10 | 2019-03-11 | 2019-03-14 | • Final product delivery
Sprint6 | Bug fixes and Prod deployemnt
Sprint7
Sprint8
Sprint9
Milestone | Delivery
Milestone 1 | 2019-01-10
Milestone 2 | 2019-02-07
Milestone 3 | 2019-03-14
Milestone 4 | 2019-03-31