## Plan
# | Task | Details | Start date | End date | Resource | Comments | status
1 | - Code integration - Services - Coding | Include new fields in Employee data as per client's request | 43482 | 43482 | Bharat
2 |  | Upload Employee and QA data from UI - End to end testng | 43480 | 43485 | Pranusha and Harish | Please try to do this in local machine , until we get aws box. I prefer doing in Pranusha's machine
3 |  | Complet the design of all the screens | 2019-01-21 | 2019-01-29 | Harish | As per the requriment
4 |  | Release survey - Employee data need to be pre-populated | 2019-01-21 | 2019-01-23 | Pranusha
5 |  | Send mail function for release survey | 2019-01-21 | 2019-01-23 | Bharat
6 |  | User Validate functioanlity | 2019-01-24 | 2019-01-25 | Pranusha
7 |  | User registration functioanlity | 2019-01-24 | 2019-01-25 | Pranusha
8 |  | User login - Google 2 phase authentication - I will come to you with detailed requirments |  |  | Pranusha
9 |  | Complete the design for Survy Q&A screens - as per the client's request | 2019-01-17 | 2019-01-20 | Harish
10 |  | Survey Q & A functionality - Database design | 2019-01-15 | 2019-01-20 | Pranusha and Bharath
11 |  | Survey Q & A functionality - Survey completion and submit | 2019-01-26 | 2019-01-28 | pranusha
12 |  | Survey Q & A functionality - Home page % display functioanlity based on the survey completion status | 2019-01-29 | 2019-02-10 | pranusha
13 |  | Survey Q & A functionality - Auto Save functionality |  |  | pranusha
14 |  | Survey Q & A functionality - Session management |  |  | pranusha
15 |  | Survey results Dashboard - for one user | 2019-01-18 | 2019-01-21 | Bharat | Work with dummy data
16 |  | Implement the save and print feature for the survery result | 2019-02-11 | 2019-02-11 | Pranusha
17 | Visualization/Reports | Company wise Reports functionality for the admin - Admin will be provided a drop-down to select the company name which he wants to view the reports and after submitting the company he will get the view of all the users or selected users reports in all the formatso Agreed formats – Tabular, Bar, spider, Pie and Radar charts | 2019-01-21 | 2019-01-29 | Bharat
18 |  | Implement below One user view – Admin can select a particular user from patricianly company All users – Admin can select all users option to get the reports of all the users User can save and print the results Combined results: comparative charts of particular industry type such as Energy/Water/Pharma/Manufacturing etc | 2019-01-30 | 2019-02-11 | Bharat
19 | Automation reports | Implement below Admin user -From backend we can schedule a job to send the reports to define set-of people – daily, weekly and monthly The report will be auto generated and distributed to the configured emails Report will be sent through mail | 2019-02-12 | 2019-02-15 | Bharat
20 | Pdf report generation | Implement below Admin user can submit a request to generate Client specific pdf report Client specific static data will be provided to us The Charts will be inserted in the defined section Report will be generated upon request | 2019-02-16 | 2019-02-24 | Bharat
21 | Testing | Testing of the complete application |  |  | All
22 | Documentation | Documentation of the complete application |  |  | kalesha | ongoing
23 | Code in GitHub | Code in GitHub of the complete application |  |  | Bharat and Kalesha | ongoing
24 | Deployment | Deployment of the complete application |  |  | All | ongoing